## Slide 1
GENBA SOPANRAO MOZE COLLEGE OF ENGINEERING, BALEWADI, PUNE
Department of Computer Engineering | Savitribai Phule Pune University (SPPU) Academic Year 2026–2027
410248: PROJECT WORK STAGE – I (REVIEW-II PRESENTATION)
OptiBuild: Resource-Constrained Construction Project Scheduling with Statutory Delay-Penalty Optimization
Project Team Members (B.E. Computer Engineering):
Bhushan V. Bhosale (4101) • Divyal Patel (4102) • Chaitanya Ghorpade (4103) • Aniket Jadhav (4104)
Under the Guidance of: Prof. [Guide Name], Department of Computer Engineering

## Slide 2
410248: PROJECT WORK STAGE – I | REVIEW-II
Presentation Outline & Structure
01. Project Context & Problem Domain
Indian real estate construction delays & MahaRERA Section 18 statutory liabilities.
02. Problem Statement & Locked Guardrails
Formal RCPSP problem formulation, NP-hardness, and strict viva boundaries.
03. SMART Project Objectives
5 measurable targets spanning CPM, GA, CP-SAT, Penalty Engine, and MobileNetV2.
04. Comprehensive Literature Survey
Synthesis of 22 peer-reviewed papers across 5 functional optimization clusters.
05. Comparative Analysis Matrix
Benchmarking existing systems (Primavera, Procore, Research GAs) vs. OptiBuild.
06. System Architecture & The Hero Module
Unified dataflow connecting NetworkX CPM, DEAP GA, OR-Tools CP-SAT, and CV.
07. Mathematical Model & Formulation
SPPU 7-Tuple Set Theory, CPM forward/backward passes, and crash slope arbitration.
08. Implementation Status & Passing Tests
Current progress with 14/14 automated Pytest unit and integration tests passing.
09. Modular Team Division & Viva Defense
Clear academic ownership split for Divyal, Chaitanya, Bhushan, and Aniket.

## Slide 3
410248: PROJECT WORK STAGE – I | REVIEW-II
Project Background & Real-World Domain Crisis
The Indian Construction Delay Crisis
• 70%+ Overruns: Empirical civil research (Doloi et al., 2012) reveals over 70% of multi-story projects in India exceed contracted completion baselines.
• Multi-Crore Capital At Stake: Projects accrue tens or hundreds of crores in buyer advances. Project managers lack dynamic algorithmic rescheduling tools.
• Static Tools Fail: Commercial software (Primavera P6, MS Project) only produces manual bar charts; they cannot automatically balance crashing costs against delay penalties.
MahaRERA Section 18: Mandatory Legal Liability
• Statutory Interest Mandate: Builders who exceed registered deadlines must compensate homebuyers monthly interest at SBI Highest MCLR + 2% per annum on total collected funds.
• The Mathematical Equation: Penalty = Amount Collected × (SBI MCLR + 2%) × (Delay Days / 365). Daily accumulation routinely exceeds tens of thousands of rupees.
• The OptiBuild Solution: Algorithmic decision engine that computes activity crash slopes vs. statutory penalties to guide builders whether to crash critical tasks or accept the penalty.

## Slide 4
410248: PROJECT WORK STAGE – I | REVIEW-II
Literature Survey & Comparative Analysis Matrix
Paper / Author | Methodology / Model | Resource | TCTP | Penalty | Exact | Identified Research Void
Hartmann (1998) | Permutation GA + SSGS | Yes | No | No | No | Makespan only; no financial crash model
Leu & Yang (1999) | Multi-Criteria GA | Yes | Yes | No | No | Two-stage leveling risks local optima
Hegazy (1999) | Discrete TCTP GA | No | Yes | No | No | Omits renewable crew capacity limits
Li & Love (1997) | Adaptive Penalty GA | No | Yes | No | No | Uses arbitrary non-legal penalty weights
Schutt et al. (2013) | Lazy Clause Gen. (LCG) | Yes | No | No | Yes | Theoretical; no business penalty logic
Sonmez (2011) | Hybrid GA + B&B | No | Yes | No | Yes | Combinatorial explosion on >100 tasks
Doloi et al. (2012) | Regression Analysis | No | No | No | No | Diagnostic survey; no scheduling tool
Jain & Prakash (2023) | Linear Programming | No | Yes | Yes* | No | Static case study; lacks rescheduling
Rashidi et al. (2024) | MobileNetV2 on Edge | No | No | No | No | Isolated vision; decoupled from CPM/GA
OptiBuild (Proposed) | DEAP GA + CP-SAT + CV | Yes | Yes | Yes** | Yes | Unified: RCPSP + MahaRERA + Vision

## Slide 5
410248: PROJECT WORK STAGE – I | REVIEW-II
Proposed Architecture: The OptiBuild Hero Module
1. CPM Precedence DAG Engine [NetworkX Directed Acyclic Graph]
Traverses topological task dependencies, computes Early/Late passes, and isolates critical float in ≤ 50 ms.
2. Resource-Constrained GA [DEAP Heuristic Scheduling]
Chromosome permutations decoded via Serial Schedule Generation Scheme (SSGS) to enforce renewable crew constraints.
3. CP-SAT Benchmark Validator [Google OR-Tools Exact Solver]
Employs interval decision variables and AddCumulative global constraints to measure the empirical GA optimality gap.
4. MahaRERA Penalty Optimizer [Statutory Delay Decision Engine]
Evaluates activity crash slope (Si) vs. SBI MCLR + 2% interest penalties to formulate concrete build acceleration advice.
5. Edge Vision Progress Verification [PyTorch MobileNetV2 Classifier]
Provides fast binary inference (< 45 ms) distinguishing Structural from Finishing phases with human review fallback.

## Slide 6
410248: PROJECT WORK STAGE – I | REVIEW-II
Mathematical Model (SPPU 7-Tuple Set Theory)
System Formal Definition: S = { I, O, F, DD, NDD, S_success, S_failure }
Inputs (I): User config (Uc), Project constraints (Creq), Task parameters (Pparams) | Outputs (O): Optimized schedule (Ropt), Benchmark metrics (Meval)
1. Critical Path Method (CPM)
ES_i = max(EF_p), EF_i = ES_i + d_i LF_i = min(LS_s), LS_i = LF_i - d_i Total Float: TF_i = LS_i - ES_i Critical Chain: TF_i = 0
2. RCPSP Resource Limit
Daily Crew Demand Bound: sum_{i in Active(t)} r_{i,k} <= R_{k,max} for all renewable crew types k across all days t in [0, T]
3. MahaRERA Statutory Penalty
Penalty_RERA = Amount Collected × (SBI MCLR + 2%) × (Delay Days / 365) Accrues daily interest liability payable to homebuyers on default
4. Activity Crash Cost Slope
Cost Slope: S_i = (C_c - C_n) / (D_n - D_c) Decision Engine Rule: If sum(S_i × Δd_i) < Penalty_RERA => CRASH TASK; Else ACCEPT PENALTY

## Slide 7
410248: PROJECT WORK STAGE – I | REVIEW-II
Team Member Modular Division & Viva Defense Split
Divyal Patel
Optimization Lead
Owned Codebase: app/engine/cpm/ app/engine/ga/
CPM Precedence DAG (NetworkX), DEAP Genetic Algorithm chromosome encoding, crossover/mutation operators, and Serial Schedule Generation Scheme (SSGS).
Chaitanya Ghorpade
Benchmark Lead
Owned Codebase: app/engine/cpsat/ app/engine/benchmark/
Google OR-Tools CP-SAT exact solver modeling, AddCumulative global constraints, and mathematical optimality gap calculation vs. heuristic GA.
Bhushan Bhosale
Financial Optimizer
Owned Codebase: app/engine/penalty/ research/ & docs/
MahaRERA Section 18 penalty computation (SBI MCLR + 2%), activity crash slope tradeoff engine, architecture specifications, and SPPU documentation.
Aniket Jadhav
Full-Stack & CV Lead
Owned Codebase: app/backend/ app/cv/ & frontend/
FastAPI REST API routes, Next.js interactive Gantt chart dashboard, and PyTorch MobileNetV2 binary progress verification model.

## Slide 8
410248: PROJECT WORK STAGE – I | REVIEW-II
Current Implementation Status & Verified Test Suite
PASS: CPM & GA Engine [app/engine/cpm/ & ga/]
Verified forward/backward pass & DEAP permutation chromosomes on 20-activity RCC benchmark dataset.
PASS: OR-Tools CP-SAT [app/engine/cpsat/]
Exact solver modeling complete with AddCumulative constraints to measure empirical optimality gap.
PASS: MahaRERA Penalty Engine [app/engine/penalty/]
Accurately compares SBI MCLR + 2% interest penalties against critical-path crash slopes.
PASS: FastAPI Backend [app/backend/routers/]
REST API routes verified for projects, tasks, schedule optimization, and progress telemetry.
PASS: MobileNetV2 Classifier [app/cv/]
Transfer learning pipeline configured for Structural vs. Finishing phase binary image inference.
PASS: SPPU Deliverables [docs/ & research/]
Stage-1 Synopsis, Report Chapter 2, IEEE conference paper draft, and Overleaf ZIP ready.
Automated Pytest Suite Status: 14 Passed, 0 Failed, 100% Green (Execution Time: ~21s)

## Slide 9
Thank You!
OptiBuild: Resource-Constrained Construction Project Scheduling with Statutory Delay-Penalty Optimization
Questions & Technical Discussion Invited